odin-lint

Implementation Roadmap

A Super Linter for the Odin Programming Language

Version 1.0  ·  2025

# 1. Overview & Goals

odin-lint is a static analysis tool for the Odin programming language. Its purpose is to enforce correctness, idiomatic patterns, and performance best practices through configurable, tiered rules — without duplicating odin fmt, odin build, or the OLS language server.

## Design Philosophy

- Correctness first — only deny-by-default rules that have zero false positives

- OLS-native — surface diagnostics through the language server, not just CLI

- Pluggable — external rule packs via YAML/TOML without recompilation

- Orthogonal — never reimplement what odin fmt, odin build, or OLS already do

- Incremental — start with 15 rock-solid rules, grow with community feedback

## Lint Tier Model (inspired by Rust Clippy)

| Tier | Default | Examples | Rationale |
| --- | --- | --- | --- |
| correctness | deny | missing defer free, double-free pattern | Clear bugs, zero false positives |
| suspicious | warn | raw pointer overuse, unreachable branches | Likely wrong, might be intentional |
| style | allow (opt-in) | naming conventions, proc length | Idiomatic Odin preferences |
| perf | allow (opt-in) | cache-unfriendly layouts, needless alloc | Data-oriented design patterns |

# 2. Architecture

odin-lint is composed of four independently testable layers. Each layer has a clean interface so components can be replaced or extended without affecting others.

| Layer | Component | Responsibility |
| --- | --- | --- |
| L1 — Parse | tree-sitter-odin (amaanq fork) | Produce AST from source files |
| L2 — Analyse | Rule Engine (core/) | Walk AST, apply rule matchers |
| L3 — Report | Formatter (output/) | Emit diagnostics: CLI, JSON, LSP |
| L4 — Integrate | OLS plugin + CI action | Surface warnings in editors and pipelines |

## Directory Structure

odin-lint/

├── core/              # Rule engine: AST walker + rule registry

├── rules/

│   ├── correctness/   # Tier 1: deny-by-default

│   ├── suspicious/    # Tier 2: warn-by-default

│   ├── style/         # Tier 3: opt-in

│   └── perf/          # Tier 4: opt-in

├── output/            # CLI, JSON, LSP diagnostic formatters

├── integrations/

│   ├── ols/           # OLS (language server) plugin

│   └── github-action/ # CI integration

├── tests/

│   ├── fixtures/      # .odin files: should_pass / should_fail

│   └── snapshots/     # Expected diagnostic output

└── docs/              # Rule documentation (one .md per rule)

# 3. Milestones

The roadmap is divided into five milestones. Each milestone ends with a gate — a set of pass/fail criteria that must be met before work begins on the next milestone. This prevents scope creep and ensures each phase ships usable value.

MILESTONE 0  ·  Foundation  ·  Estimated: 2–3 weeks

Goal: A working skeleton — parse an Odin file, walk its AST, emit one diagnostic. No rules, no config, no integrations. Prove the pipeline works end to end.

### Tasks

- Set up repo: directory structure, README, MIT licence, CI skeleton (GitHub Actions)

- Choose and pin tree-sitter-odin fork (recommend amaanq/tree-sitter-odin — most active)

- Write an AST walker that visits every node in a file

- Implement the diagnostic struct: { file, line, col, rule_id, tier, message, fix? }

- Write a stub rule: warn on any procedure named TODO_FIXME (purely for pipeline validation)

- CLI: odin-lint <file> prints diagnostics to stdout

- Test harness: fixture files in tests/fixtures/pass/ and tests/fixtures/fail/, runner compares output to snapshots

### Tests for M0

| Test | Pass Condition |
| --- | --- |
| AST walker visits all nodes | Node count matches expected count for each fixture file |
| Stub rule fires correctly | Exactly one diagnostic emitted for fixture with TODO_FIXME proc |
| Clean file produces zero output | Empty stdout on a known-good .odin file |
| CLI exit codes | Exit 0 on clean, exit 1 on any correctness finding |
| Snapshot test runner works | CI fails if snapshot differs from actual output |

GATE 0 — Must pass all 5 tests above before starting M1

MILESTONE 1  ·  Correctness Tier (Core Rules)  ·  Estimated: 4–6 weeks

Goal: Ship the 'correctness' rule tier — rules that are deny-by-default and must have zero false positives. These form the trust foundation of the tool. If any of these fire incorrectly, the whole tool loses credibility.

### Target Rules (Correctness Tier — 8 rules)

| Rule ID | Pattern Detected | Source Inspiration |
| --- | --- | --- |
| C001 | Allocation without matching defer free in same scope | Rust: clippy::mem_forget |
| C002 | defer free on wrong pointer (double-free risk) | C: AddressSanitizer |
| C003 | context.allocator swapped inside a proc but not restored | Odin-specific |
| C004 | Unreachable code after return / break | Java: FindBugs UC_USELESS_CONDITION |
| C005 | Shadowed variable silently overrides outer binding | Rust: clippy::shadow_reuse |
| C006 | Loop variable captured in closure/proc literal | Go vet: loopclosure |
| C007 | Integer cast narrowing without explicit check | Zig: integer overflow safety |
| C008 | Slice bounds not validated before index | Odin-specific runtime safety |

### Tasks

- Implement rule registry: rules self-register, engine iterates all active rules per AST node

- Implement each rule as a separate file in rules/correctness/ with: matcher(), message(), fix_hint()

- Write at least 3 fixture pairs (pass + fail) per rule = 48 fixture files minimum

- Add --rule=C001 flag to run a single rule (crucial for debugging)

- Add --fix flag that prints fix hints (no auto-apply yet)

- Write rule documentation: docs/correctness/C001.md ... C008.md (one per rule)

### Tests for M1

| Test | Pass Condition |
| --- | --- |
| Zero false positives | All pass/ fixtures produce zero diagnostics for all 8 rules |
| All true positives fire | All fail/ fixtures produce exactly the documented diagnostic |
| Rule isolation | Disabling a rule via config produces no output for its fixtures |
| Fix hints present | --fix flag produces a non-empty hint for every correctness rule |
| Snapshot stability | Re-running on unchanged files produces byte-identical output |
| No rule duplicates odin build | Run odin build on every fixture; no rule fires on errors the compiler already catches |

GATE 1 — Zero false positives on correctness tier. 100% fixture coverage. No duplication of compiler errors.

MILESTONE 2  ·  Config + Suspicious/Style Tiers  ·  Estimated: 3–4 weeks

Goal: Make the tool configurable and add the two opt-in tiers. Users can now tailor odin-lint to their project's standards via an odin-lint.toml config file.

### Config File Design

# odin-lint.toml

[lint]

tiers = ["correctness", "suspicious"]  # enabled tiers

[rules]

C003.severity = "warn"   # downgrade a correctness rule

S012.enabled  = false    # disable a style rule

[paths]

exclude = ["vendor/", "generated/"]

### Target Rules (Suspicious — 5 rules, Style — 4 rules)

| Rule ID | Tier | Pattern | Notes |
| --- | --- | --- | --- |
| S001 | susp | Raw pointer []^T where []T would suffice | Common Odin newcomer mistake |
| S002 | susp | Empty when branch in switch | Usually a logic error |
| S003 | susp | Proc with >5 return values | Suggests struct refactor needed |
| S004 | susp | Allocator passed as param but never used | Dead parameter |
| S005 | susp | Boolean param that controls fundamentally different paths | Clippy: fn_bool_param |
| T001 | style | Proc name does not follow snake_case | Odin convention |
| T002 | style | Type name does not follow PascalCase | Odin convention |
| T003 | style | Proc body exceeds 80 lines | Complexity threshold |
| T004 | style | Magic number (untyped integer literal not 0/1) | Readability |

### Tasks

- Config parser: read odin-lint.toml, merge with CLI flags (CLI overrides file)

- Implement 5 suspicious + 4 style rules with full fixture coverage

- --explain <rule_id> flag: prints full description + example + fix hint

- JSON output mode: --format=json for CI integration

- Path exclusion logic from config

### Tests for M2

| Test | Pass Condition |
| --- | --- |
| Config loading | All TOML fields parse correctly; malformed TOML exits with clear error |
| Style tier disabled by default | Style rules produce no output unless explicitly enabled |
| Rule downgrade via config | C003 set to warn does not cause non-zero exit code |
| Path exclusion | Files matching exclude patterns produce zero diagnostics |
| JSON output is valid | JSON schema validated by fixture runner on all outputs |
| --explain completeness | Every rule has a non-empty --explain entry |

GATE 2 — Config parser fully tested. Style tier off by default and verifiably so. JSON output valid against schema.

MILESTONE 3  ·  OLS Integration + Auto-fix  ·  Estimated: 3–5 weeks

Goal: Diagnostics appear inline in VS Code and Neovim via OLS. Selected rules gain auto-fix capability. This is the milestone that makes odin-lint feel like a first-class development tool rather than a CLI script.

### OLS Integration Approach

OLS (ols) supports custom diagnostic providers via its plugin system. odin-lint will run as a subprocess that OLS spawns, communicating over stdin/stdout using a minimal JSON protocol mirroring LSP's PublishDiagnostics format.

- odin-lint --lsp-mode: runs in long-lived subprocess mode, reads file change events from stdin, emits diagnostic JSON to stdout

- OLS plugin (integrations/ols/): configures OLS to spawn odin-lint and forward its diagnostics

- Diagnostic severity maps: correctness → Error, suspicious → Warning, style/perf → Hint

- Code actions: for rules with fix hints, expose an LSP code action (quick fix) in the editor

### Auto-fix Rules (Phase 1 — safe transformations only)

| Rule | Before | After (auto-fix) |
| --- | --- | --- |
| C001 | buf := make([]u8, 1024) | buf := make([]u8, 1024) defer delete(buf) |
| T001 | proc MyProc() {} | proc my_proc() {} |
| T002 | my_type :: struct {} | My_Type :: struct {} |
| C004 | return x foo() // unreachable | return x // (dead code removed) |

### Tasks

- Implement --lsp-mode with JSON diagnostic protocol

- Write and publish OLS plugin configuration (integrations/ols/README.md + config snippet)

- Test OLS integration in VS Code (odin-lsp extension) and Neovim (nvim-lspconfig)

- Implement --fix --apply flag: modifies files in-place with confirmation prompt

- Fix safety: never apply a fix that changes semantics — fixable rules have an explicit safe_fix = true marker

- Add odin-lint check command: like lint but exits 0 if only style/perf findings (useful for CI gates)

### Tests for M3

| Test | Pass Condition |
| --- | --- |
| LSP mode starts and stays alive | Process remains running after 100 sequential file-change events |
| Diagnostic positions are correct | Line/col in LSP output matches the actual problematic token, verified by editor screenshot fixture |
| Auto-fix round-trips cleanly | Apply fix → re-lint → zero findings for that rule on same file |
| Fix does not corrupt files | odin build passes on all auto-fixed fixtures |
| VS Code integration smoke test | Opening a fail/ fixture in VS Code shows red/yellow squiggles at correct positions |
| No fix applied without --apply | --fix alone only prints diff, does not modify files on disk |

GATE 3 — OLS integration smoke-tested in at least 2 editors. Auto-fix round-trip passes for all 4 rules. No file corruption.

MILESTONE 4  ·  Perf Tier + GitHub Action + Community Release  ·  Estimated: 3–4 weeks

Goal: Add the performance/data-oriented rules, publish a GitHub Action, and release v1.0 publicly with full documentation. This is the public launch milestone.

### Target Rules (Performance Tier — 4 rules)

| Rule ID | Pattern | Why It Matters for Odin |
| --- | --- | --- |
| P001 | Struct fields ordered suboptimally (padding waste) | Odin's target audience does low-level, cache-sensitive code |
| P002 | AOS layout where SOA would be cache-friendlier | Core data-oriented design pattern — unique to Odin tooling |
| P003 | Allocation inside a hot loop | make/new inside for loop without pool/arena |
| P004 | context.temp_allocator used outside a temp scope | Temp allocator leaks if free_all not called correctly |

### GitHub Action

# .github/workflows/lint.yml

- uses: odin-lang/odin-lint-action@v1

with:

tiers: correctness,suspicious

fail-on: correctness

### Documentation Requirements for v1.0

- README: install, quick start, config reference

- Rule catalogue: one page per rule (rule ID, description, bad example, good example, fix hint, rationale)

- Contributing guide: how to write a new rule (template + checklist)

- CHANGELOG.md with semantic versioning from v0.1 onward

- Integration guide: VS Code, Neovim, Helix, CI

### Tests for M4

| Test | Pass Condition |
| --- | --- |
| P001–P004 fixture coverage | 3 pass + 3 fail fixtures per rule, all passing |
| GitHub Action end-to-end | Action runs on a test repo, fails on correctness finding, passes on clean repo |
| Documentation completeness | Every rule ID has a matching docs/ entry; CI enforces this |
| Install test | Fresh install on Linux, macOS, Windows (WSL) and run odin-lint --version |
| Performance benchmark | odin-lint on the Odin standard library source completes in under 5 seconds |
| No regression on prior milestones | Full test suite (all milestones) passes green |

GATE 4 (v1.0 Release Gate) — Full test suite green. Docs complete. GitHub Action published. Perf benchmark under 5s on stdlib.

# 4. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| tree-sitter-odin fork diverges or goes unmaintained | Medium | Blocks all AST work | Pin to a specific commit hash; contribute upstream; keep parser adapter isolated behind an interface so it can be swapped |
| Odin language changes break AST assumptions | Low (language is stable) | Rule rewrites needed | Bill declared spec complete; monitor odin-lang/Odin releases; add a nightly CI run against latest Odin |
| Correctness rules produce false positives post-release | Medium | Loss of user trust | Strict Gate 1 process; public rule disable mechanism; fast patch release process (< 48h) |
| OLS plugin API changes | Medium | M3 rework needed | Keep LSP mode self-contained; document the protocol so it works with other editors too |
| Low community adoption | Medium | Reduces feedback quality | Announce on Odin Discord early (even at M1); invite rule contributions before v1.0; keep install dead-simple |

# 5. Summary Timeline

| Milestone | Focus | Duration | Exit Gate |
| --- | --- | --- | --- |
| M0 | Foundation: pipeline + AST walker | 2–3 weeks | 5 pipeline tests pass |
| M1 | Correctness tier (8 rules) | 4–6 weeks | Zero false positives, full fixture coverage |
| M2 | Config + Suspicious/Style tiers | 3–4 weeks | Config tested, style off by default |
| M3 | OLS integration + auto-fix | 3–5 weeks | 2-editor smoke test, fix round-trip |
| M4 | Perf tier + GH Action + v1.0 | 3–4 weeks | Full suite green, docs complete, <5s bench |
| Total |  | 15–22 weeks | v1.0 public release |

# 6. Definition of Done (for each Rule)

Every rule — regardless of tier — must satisfy all of the following before it is merged:

- Rule file: rules/<tier>/<ID>.odin with matcher(), message(), and fix_hint() implemented

- Documentation: docs/<tier>/<ID>.md with description, bad example, good example, rationale, and inspiration source

- Fixtures: minimum 3 pass/ and 3 fail/ .odin files covering edge cases

- Snapshot: expected diagnostic output committed and verified by CI

- Orthogonality check: manually confirmed that odin build does NOT already report this error

- False positive review: at least 50 lines of real-world Odin code (from odin-lang/Odin stdlib) tested with no spurious firing

- --explain entry: non-empty output for odin-lint --explain <ID>

# 7. Community Integration

odin-lint is most valuable if the community contributes rules. The rule system is designed for this from day one.

- Announce at M1 on the Odin Discord (#tooling channel) — invite early adopters and false-positive reports

- Rule proposal template: GitHub issue template for new rule requests (tier, pattern, rationale, example)

- Rule bounties: tag 'help wanted' rules with estimated effort (S/M/L)

- Integration request tracker: track editor integration requests — prioritise editors with active Odin communities

- Versioned rule sets: allow projects to pin to a rule set version so upgrades don't break CI unexpectedly

odin-lint Roadmap v1.0  ·  Built for the Odin community